## Slide 1
INVESTMENT COMMITTEE PACK
Marina Tower
Mixed-use waterfront asset · Corniche, Doha
Bohio RE Fund II · Q2 2026 review
Prepared for the Investment Committee · Strictly confidential

## Slide 2
RECOMMENDATION
Continue to fund, with a cost review
The asset remains on plan for value. Sales are ahead of underwriting on price; delivery is two points behind programme and final cost is tracking 1.2% above sanction.
SAR 182M
Independent valuation
Knight Frank, Apr 2026
18.2%
Project IRR
At a 6.50% exit cap
58%
Units sold
186 of 320 · 24 reserved
+1.2%
Cost vs sanction
SAR 992.0M against 980.0M
THE DECISION SOUGHT
Approve the remaining SAR 408.6M cost to complete, and a supplementary contingency of SAR 10.0M.
Settle variation VO-021 by negotiation before it escalates to formal dispute.

## Slide 3
THE ASSET
What we own
LOCATION
Corniche, Doha — waterfront
FORM
28 storeys · 320 residential units over a retail podium
STATUS
Phase 2 of 6 · superstructure at Level 12 of 28
TENURE
Freehold · building permit issued Aug 2025
CONTRACTOR
Al-Bawani · GMP SAR 145.0M hard cost · 30-month programme
HANDOVER
Targeted March 2028
Anchor retail let to Doha Marine Retail — 4,600 sqm at SAR 4.14M p.a., 12-year term

## Slide 4
CAPITAL STRUCTURE
The joint venture
Committed equity of SAR 294.0M, subscribed 65 / 35 between the Sponsor and the Partner.
Bohio RE Fund II — Sponsor
65%
SAR 191.1M
Doha Ventures Holding — Partner
35%
SAR 102.9M
RESERVED MATTERS
Disposals above SAR 25.0M
Leverage beyond 60% LTV
Budget variance beyond 7.5%
DISTRIBUTION WATERFALL
1
Repay shareholder loans with accrued interest
2
Return subscribed capital, pro rata
3
8% preferred return, compounded
4
80 / 20 split thereafter — 20% carry to the Sponsor

## Slide 5
DEVELOPMENT & COST
Tracking 1.2% above sanction
Cost manager: Turner International · SAP cost centre PRJ-MAR-2026 · reporting April 2026
980.0
Sanctioned budget
740.0
Committed
583.4
Actual to date
992.0
Anticipated final cost
SAR millions
VARIANCE TO SANCTION
+ SAR 12.0M
+1.2% · two variations still outside this figure
WHAT DROVE IT
Façade re-tender
SAR 7.4M
MEP re-coordination
SAR 3.1M
Marine works provisional
SAR 1.5M
Contingency: SAR 8.3M left of 29.4M — thin for 58% of works remaining

## Slide 6
SALES & ABSORPTION
Ahead of underwriting on price
186
Units sold
of 320 · 58%
SAR 2,150
Achieved per sqft
vs SAR 2,080 list · +3.4%
12 / mo
Absorption
14 last month on Tower B
Q3 2027
Sell-out forecast
at current run-rate
UNIT DISPOSITION
Sold — 186 units
58%
Reserved — 24 units
8%
Remaining — 110 units
34%
Contracted sales revenue SAR 512M, of which SAR 388M collected — a 76% collection rate.
A 5% payment-plan incentive is live on Tower B stock; buyer pipeline is 140 active leads.

## Slide 7
VALUATION & RETURNS
Sensitive to the exit cap
Market value of SAR 182.0M — stabilised NOI of SAR 11.8M capitalised at 6.50%.
SAR 189M
6.25% exit cap
SAR 182M
6.50% base case
SAR 175M
6.75% exit cap
Market value by capitalisation rate
RETURNS AT BASE CASE
Project IRR
18.2%
Equity multiple
2.2x
Yield on cost
6.4%
DSCR
1.42x
At a 7.00% exit: IRR 16.7%, multiple 2.0x
Trading below underwriting: occupancy 90% against 93%, opex 31% of EGI against 28%. Current-year NOI of SAR 7.6M reflects a pre-stabilisation position.

## Slide 8
RISK
What we are watching
Cost overrun
AFC SAR 992.0M against SAR 980.0M sanctioned, with two variations outstanding.
MITIGATION
Supplementary contingency of SAR 10.0M; settle VO-021 by negotiation at ~SAR 1.9M.
Programme slippage
42% complete against 44% programmed — two points behind.
MITIGATION
Recovery plan agreed with Al-Bawani, tracked weekly; re-baseline the schedule.
Exit cap widening
A 50bp move to 7.00% takes IRR from 18.2% to 16.7%.
MITIGATION
Hold-period flexibility under the JV; no forced sale before Year 6.
Operating gap
Occupancy 90% and opex 31% of EGI, both behind underwriting.
MITIGATION
Asset-management plan to close the gap ahead of stabilisation.

## Slide 9
THE ASK
Three approvals sought
01
Fund the remaining cost to complete
SAR 408.6M, taking the anticipated final cost to SAR 992.0M.
02
Approve a supplementary contingency
SAR 10.0M — the residual SAR 8.3M is thin for the works remaining.
03
Authorise settlement of VO-021
Negotiate at approximately SAR 1.9M against SAR 3.2M submitted.
Bohio RE Fund II · Investment Committee · Q2 2026 · Strictly confidential