## Inputs
NORTHGATE DATA CENTRE CAMPUS – DEVELOPMENT AND HOLD (USD)
Case (1 Base, 2 Downside, 3 Upside) | 1
Model start | 2026-12-31
Capex per MW ($, today) | 11500000
Cost inflation a year | 3%
Rent per kW a month ($) · Base | 118
Rent per kW a month ($) · Downside | 102
Rent per kW a month ($) · Upside | 130
Rent escalation a year | 2.5%
PUE | 1.35
Power tariff ($ per MWh) | 85
IT load utilisation | 70%
Power cost recovered from tenants | 90%
Other operating cost (% of rent) | 8%
Construction loan to cost | 65%
Construction loan rate | 8.5%
Conversion trigger (occupancy) | 85%
Mini-perm rate | 6.25%
Mini-perm amortisation a year | 2%
Cash sweep above DSCR | 1.4
Cash sweep share | 50%
Exit quarter | 36
Exit cap · Base | 6.25%
Exit cap · Downside | 7%
Exit cap · Upside | 5.75%
Rent per kW (live case) | 118
Exit cap (live case) | 6.25%

## Phases
Phase | MW | Start quarter | Build (quarters) | Pre-let · Base | Pre-let · Downside | Pre-let · Upside | Lease-up of the rest (quarters) | Pre-let (live case)
Phase 1 | 24 | 1 | 7 | 0.6 | 0.4 | 0.75 | 6 | 0.6
Phase 2 | 32 | 6 | 8 | 0.5 | 0.3 | 0.65 | 8 | 0.5
Phase 3 | 40 | 13 | 8 | 0.35 | 0.2 | 0.5 | 10 | 0.35

## Cash Flow
Quarter | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Date | 2026-12-31 | 2027-03-31 | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31 | 2029-03-31 | 2029-06-30 | 2029-09-30 | 2029-12-31 | 2030-03-31 | 2030-06-30 | 2030-09-30 | 2030-12-31 | 2031-03-31 | 2031-06-30 | 2031-09-30 | 2031-12-31 | 2032-03-31 | 2032-06-30 | 2032-09-30 | 2032-12-31 | 2033-03-31 | 2033-06-30 | 2033-09-30 | 2033-12-31 | 2034-03-31 | 2034-06-30 | 2034-09-30 | 2034-12-31 | 2035-03-31 | 2035-06-30 | 2035-09-30 | 2035-12-31 | 2036-03-31 | 2036-06-30 | 2036-09-30 | 2036-12-31
P1 capex | 0 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P1 leased MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 17.6 | 19.2 | 20.8 | 22.4 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
P1 rent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5664000 | 6230400 | 6796800 | 7363200 | 8127840 | 8708400 | 8708400 | 8708400 | 8926110 | 8926110 | 8926110 | 8926110 | 9149262.75 | 9149262.75 | 9149262.75 | 9149262.75 | 9377994.3187 | 9377994.3187 | 9377994.3187 | 9377994.3187 | 9612444.1767 | 9612444.1767 | 9612444.1767 | 9612444.1767 | 9852755.2811 | 9852755.2811 | 9852755.2811 | 9852755.2811 | 10099074.1632 | 10099074.1632 | 10099074.1632 | 10099074.1632 | 10351551.0172
P2 capex | 0 | 0 | 0 | 0 | 0 | 0 | 47380000 | 47380000 | 47380000 | 47380000 | 47380000 | 47380000 | 47380000 | 47380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P2 leased MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 22 | 24 | 26 | 28 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
P2 rent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6372000 | 7080000 | 7788000 | 8496000 | 9434100 | 10159800 | 10885500 | 11611200 | 11901480 | 11901480 | 11901480 | 11901480 | 12199017 | 12199017 | 12199017 | 12199017 | 12503992.425 | 12503992.425 | 12503992.425 | 12503992.425 | 12816592.2356 | 12816592.2356 | 12816592.2356 | 12816592.2356 | 13137007.0415 | 13137007.0415 | 13137007.0415
P3 capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P3 leased MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6 | 19.2 | 21.8 | 24.4 | 27 | 29.6 | 32.2 | 34.8 | 37.4 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
P3 rent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5876400 | 6796800 | 7717200 | 8637600 | 9796950 | 10740360 | 11683770 | 12627180 | 13909854.75 | 14876850 | 14876850 | 14876850 | 15248771.25 | 15248771.25 | 15248771.25 | 15248771.25 | 15629990.5312 | 15629990.5312 | 15629990.5312 | 15629990.5312
Capex | 0 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 39428571.4286 | 86808571.4286 | 86808571.4286 | 47380000 | 47380000 | 47380000 | 47380000 | 47380000 | 110211802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 62831802.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MW built | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 56 | 56 | 56 | 56 | 56 | 56 | 56 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96
Leased MW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 17.6 | 19.2 | 20.8 | 22.4 | 24 | 42 | 44 | 46 | 48 | 50 | 52 | 54 | 72.6 | 75.2 | 77.8 | 80.4 | 83 | 85.6 | 88.2 | 90.8 | 93.4 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96 | 96
Occupancy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.73333 | 0.8 | 0.86667 | 0.93333 | 1 | 0.75 | 0.78571 | 0.82143 | 0.85714 | 0.89286 | 0.92857 | 0.96429 | 0.75625 | 0.78333 | 0.81042 | 0.8375 | 0.86458 | 0.89167 | 0.91875 | 0.94583 | 0.97292 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Rent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5664000 | 6230400 | 6796800 | 7363200 | 8127840 | 8708400 | 15080400 | 15788400 | 16714110 | 17422110 | 18360210 | 19085910 | 20034762.75 | 26636862.75 | 27847542.75 | 28767942.75 | 29917074.3188 | 31076424.3188 | 32317371.3188 | 33260781.3188 | 34438641.1767 | 35721315.9267 | 36993286.6017 | 36993286.6017 | 37233597.7061 | 37605518.9561 | 37918118.7668 | 37918118.7668 | 38164437.6488 | 38545656.93 | 38866071.7359 | 38866071.7359 | 39118548.59
Power cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814588 | 3096046.8 | 3377505.6 | 3658964.4 | 3940423.2 | 4221882 | 7388293.5 | 7740117 | 8091940.5 | 8443764 | 8795587.5 | 9147411 | 9499234.5 | 12771193.05 | 13228563.6 | 13685934.15 | 14143304.7 | 14600675.25 | 15058045.8 | 15515416.35 | 15972786.9 | 16430157.45 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528 | 16887528
Power recovered | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533129.2 | 2786442.12 | 3039755.04 | 3293067.96 | 3546380.88 | 3799693.8 | 6649464.15 | 6966105.3 | 7282746.45 | 7599387.6 | 7916028.75 | 8232669.9 | 8549311.05 | 11494073.745 | 11905707.24 | 12317340.735 | 12728974.23 | 13140607.725 | 13552241.22 | 13963874.715 | 14375508.21 | 14787141.705 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2 | 15198775.2
Other opex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453120 | 498432 | 543744 | 589056 | 650227.2 | 696672 | 1206432 | 1263072 | 1337128.8 | 1393768.8 | 1468816.8 | 1526872.8 | 1602781.02 | 2130949.02 | 2227803.42 | 2301435.42 | 2393365.9455 | 2486113.9455 | 2585389.7055 | 2660862.5055 | 2755091.2941 | 2857705.2741 | 2959462.9281 | 2959462.9281 | 2978687.8165 | 3008441.5165 | 3033449.5013 | 3033449.5013 | 3053155.0119 | 3083652.5544 | 3109285.7389 | 3109285.7389 | 3129483.8872
NOI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4929421.2 | 5422363.32 | 5915305.44 | 6408247.56 | 7083570.48 | 7589539.8 | 13135138.65 | 13751316.3 | 14567787.15 | 15183964.8 | 16011834.45 | 16644296.1 | 17482058.28 | 23228794.425 | 24296882.97 | 25097913.915 | 26109377.9033 | 27130242.8483 | 28226177.0333 | 29048377.1782 | 30086271.1926 | 31220594.9076 | 32345070.8736 | 32345070.8736 | 32566157.0896 | 32908324.6396 | 33195916.4654 | 33195916.4654 | 33422529.8369 | 33773251.5756 | 34068033.1971 | 34068033.1971 | 34300311.9028
Converted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Opening loan | 0 | 0 | 25628571.4286 | 51801750 | 78531108.6161 | 105828466.1027 | 133705892.436 | 192972714.0788 | 253498955.6816 | 289682808.4898 | 326635568.1702 | 364373573.9938 | 393348706.1239 | 422178962.5932 | 491705739.4053 | 530087882.3332 | 568278114.5466 | 606277395.5989 | 644086680.2459 | 681706918.4696 | 719139055.5023 | 756384031.8498 | 751908008.9378 | 746855699.2872 | 741355192.9917 | 735297043.674 | 728671288.0995 | 721435034.8643 | 713719389.4167 | 705411980.5581 | 696459008.6708 | 686859305.1283 | 677169004.3837 | 667276708.3177 | 657119969.9327 | 646723581.4162 | 636229076.9831 | 0 | 0 | 0 | 0
Loan draw | 0 | 25628571.4286 | 25628571.4286 | 25628571.4286 | 25628571.4286 | 25628571.4286 | 56425571.4286 | 56425571.4286 | 30797000 | 30797000 | 30797000 | 30797000 | 30797000 | 71637671.625 | 40840671.625 | 40840671.625 | 40840671.625 | 40840671.625 | 40840671.625 | 40840671.625 | 40840671.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest capitalised | 0 | 0 | 544607.1429 | 1100787.1875 | 1668786.0581 | 2248854.9047 | 2841250.2143 | 4100670.1742 | 5386852.8082 | 6155759.6804 | 6941005.8236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest paid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5693337.0937 | 6146073.5332 | 6596546.2905 | 7682902.1782 | 8282623.1615 | 8879345.5398 | 9473084.3062 | 10063854.3788 | 10651670.6011 | 11236547.7422 | 11818500.4977 | 11748562.6397 | 11669620.3014 | 11583674.8905 | 11489016.3074 | 11385488.8766 | 11272422.4198 | 11151865.4596 | 11022062.1962 | 10882172.0105 | 10732176.6426 | 10580765.6935 | 10426198.5675 | 10267499.5302 | 10105055.9596 | 9941079.3279 | 0 | 0 | 0 | 0
Amortisation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1821867.87 | 1966743.5306 | 2110894.813 | 2458528.697 | 2650439.4117 | 2841390.5727 | 3031386.978 | 3220433.4012 | 3408534.5923 | 3595695.2775 | 3781920.1592 | 3759540.0447 | 3734278.4964 | 3706775.965 | 3676485.2184 | 3643356.4405 | 3607175.1743 | 3568596.9471 | 3527059.9028 | 3482295.0434 | 3434296.5256 | 3385845.0219 | 3336383.5416 | 3285599.8497 | 3233617.9071 | 3181145.3849 | 0 | 0 | 0 | 0
DSCR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8527 | 0.87313 | 0.87162 | 1.2952 | 1.2578 | 1.2429 | 1.2143 | 1.2053 | 1.1838 | 1.1787 | 1.489 | 1.5667 | 1.6293 | 1.7076 | 1.7889 | 1.8781 | 1.9522 | 2.0438 | 2.1459 | 2.2517 | 2.2832 | 2.3317 | 2.3911 | 2.4493 | 2.4887 | 2.547 | 0 | 0 | 0 | 0
Cash sweep | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694102.7527 | 1292769.606 | 1766227.799 | 2351373.3528 | 2949270.3561 | 3592896.7947 | 4108470.2733 | 4738811.9116 | 5425911.9845 | 6117408.4991 | 6256004.219 | 6506451.044 | 6820354.8435 | 7110788.6668 | 7260886.526 | 0 | 0 | 0 | 0 | 0
Loan balance | 0 | 25628571.4286 | 51801750 | 78531108.6161 | 105828466.1027 | 133705892.436 | 192972714.0788 | 253498955.6816 | 289682808.4898 | 326635568.1702 | 364373573.9938 | 393348706.1239 | 422178962.5932 | 491705739.4053 | 530087882.3332 | 568278114.5466 | 606277395.5989 | 644086680.2459 | 681706918.4696 | 719139055.5023 | 756384031.8498 | 751908008.9378 | 746855699.2872 | 741355192.9917 | 735297043.674 | 728671288.0995 | 721435034.8643 | 713719389.4167 | 705411980.5581 | 696459008.6708 | 686859305.1283 | 677169004.3837 | 667276708.3177 | 657119969.9327 | 646723581.4162 | 636229076.9831 | 0 | 0 | 0 | 0 | 0
Sale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161488100.8408 | 0 | 0 | 0 | 0
Loan repaid at sale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633047931.5982 | 0 | 0 | 0 | 0
Equity in | 0 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 30383000 | 30383000 | 16583000 | 16583000 | 16583000 | 16583000 | 16583000 | 38574130.875 | 21991130.875 | 21991130.875 | 21991130.875 | 21991130.875 | 21991130.875 | 21991130.875 | 21991130.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity cash flow | 0 | -13800000 | -13800000 | -13800000 | -13800000 | -13800000 | -30383000 | -30383000 | -11653578.8 | -11160636.68 | -10667694.56 | -17689957.4036 | -17612246.5838 | -39692032.1785 | -18997423.1002 | -19172877.1481 | -19144079.8375 | -19311637.3592 | -19263584.2051 | -19407039.9684 | -19341315.6147 | 6934271.0154 | 7496010.6797 | 7927787.3182 | 8467553.695 | 9015470.9664 | 9604434.9215 | 10060309.3109 | 10626996.8743 | 11245560.8241 | 11863195.3206 | 11922593.4863 | 12093095.3302 | 12325387.6871 | 12532028.4188 | 12596356.0727 | 1548740474.3667 | 0 | 0 | 0 | 0
Project cash flow | 0 | -39428571.4286 | -39428571.4286 | -39428571.4286 | -39428571.4286 | -39428571.4286 | -86808571.4286 | -86808571.4286 | -42450578.8 | -41957636.68 | -41464694.56 | -40971752.44 | -40296429.52 | -102622262.7 | -49696663.85 | -49080486.2 | -48264015.35 | -47647837.7 | -46819968.05 | -46187506.4 | -45349744.22 | 23228794.425 | 24296882.97 | 25097913.915 | 26109377.9033 | 27130242.8483 | 28226177.0333 | 29048377.1782 | 30086271.1926 | 31220594.9076 | 32345070.8736 | 32345070.8736 | 32566157.0896 | 32908324.6396 | 33195916.4654 | 33195916.4654 | 2194910630.6776 | 0 | 0 | 0 | 0

## Returns
Levered IRR | 27.48%
Project IRR | 16.91%
Equity multiple | 4.5684
Peak debt ($) | 756384031.8498
Minimum DSCR (after conversion) | 0.8527
Conversion quarter | 11
Total development cost ($) | 1157694420
Yield on cost (exit-year NOI) | 11.55%
Exit value ($) | 2161488100.8408
Net profit ($) | 1330571422.8486
Cash swept ($) | 66991728.629