## Inputs
DUBAI CREEK TOWER PODIUM – CONTRACTOR TENDER (AED)
Start date | 2027-01-31
Programme (months) | 22
Overhead and profit mark-up | 11%
Retention | 10%
Defects liability period (months) | 12
Client pays after (days) | 60
Liquidated damages a month (% of contract) | 0.5%
LD cap (% of contract) | 10%
Delay (months) | 0
Change orders (% of contract) | 4%
Discount rate a year | 9%
Advance payment | 10%

## BOQ
Item | Quantity | Unit rate (AED) | Trade | Cost (AED)
Piling | 18500 | 1150 | Substructure | 21275000
Raft | 9200 | 2650 | Substructure | 24380000
Frame | 41000 | 1820 | Structure | 74620000
Facade | 26500 | 2400 | Envelope | 63600000
MEP | 1 | 98000000 | Services | 98000000
Fit-out | 33000 | 1350 | Finishes | 44550000
External works | 1 | 14000000 | Externals | 14000000

## Curve
Share of programme | Cumulative work
0 | 0
0.1 | 0.03
0.2 | 0.09
0.3 | 0.18
0.4 | 0.3
0.5 | 0.44
0.6 | 0.58
0.7 | 0.71
0.8 | 0.83
0.9 | 0.93
1 | 1

## Cash Flow
Month | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Date | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | 2028-12-31 | 2029-01-31 | 2029-02-28 | 2029-03-31 | 2029-04-30 | 2029-05-31 | 2029-06-30 | 2029-07-31 | 2029-08-31 | 2029-09-30 | 2029-10-31 | 2029-11-30 | 2029-12-31 | 2030-01-31 | 2030-02-28 | 2030-03-31 | 2030-04-30 | 2030-05-31 | 2030-06-30 | 2030-07-31 | 2030-08-31 | 2030-09-30
Share of programme | 0 | 0.045455 | 0.090909 | 0.13636 | 0.18182 | 0.22727 | 0.27273 | 0.31818 | 0.36364 | 0.40909 | 0.45455 | 0.5 | 0.54545 | 0.59091 | 0.63636 | 0.68182 | 0.72727 | 0.77273 | 0.81818 | 0.86364 | 0.90909 | 0.95455 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cumulative work | 0 | 0.013636 | 0.027273 | 0.051818 | 0.079091 | 0.11455 | 0.15545 | 0.20182 | 0.25636 | 0.31273 | 0.37636 | 0.44 | 0.50364 | 0.56727 | 0.62727 | 0.68636 | 0.74273 | 0.79727 | 0.84818 | 0.89364 | 0.93636 | 0.96818 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cost incurred | 0 | 4827845.4545 | 4827845.4545 | 8690121.8182 | 9655690.9091 | 12552398.1818 | 14483536.3636 | 16414674.5455 | 19311381.8182 | 19955094.5455 | 22529945.4545 | 22529945.4545 | 22529945.4545 | 22529945.4545 | 21242520 | 20920663.6364 | 19955094.5455 | 19311381.8182 | 18023956.3636 | 16092818.1818 | 15127249.0909 | 11264972.7273 | 11264972.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Valuation | 0 | 5358908.4545 | 5358908.4545 | 9646035.2182 | 10717816.9091 | 13933161.9818 | 16076725.3636 | 18220288.7455 | 21435633.8182 | 22150154.9455 | 25008239.4545 | 25008239.4545 | 25008239.4545 | 25008239.4545 | 23579197.2 | 23221936.6364 | 22150154.9455 | 21435633.8182 | 20006591.5636 | 17863028.1818 | 16791246.4909 | 12504119.7273 | 12504119.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advance recovery | 0 | 535890.8455 | 535890.8455 | 964603.5218 | 1071781.6909 | 1393316.1982 | 1607672.5364 | 1822028.8745 | 2143563.3818 | 2215015.4945 | 2500823.9455 | 2500823.9455 | 2500823.9455 | 2500823.9455 | 2357919.72 | 2322193.6636 | 2215015.4945 | 2143563.3818 | 2000659.1564 | 1786302.8182 | 1679124.6491 | 1250411.9727 | 1250411.9727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held | 0 | 535890.8455 | 535890.8455 | 964603.5218 | 1071781.6909 | 1393316.1982 | 1607672.5364 | 1822028.8745 | 2143563.3818 | 2215015.4945 | 2500823.9455 | 2500823.9455 | 2500823.9455 | 2500823.9455 | 2357919.72 | 2322193.6636 | 2215015.4945 | 2143563.3818 | 2000659.1564 | 1786302.8182 | 1679124.6491 | 1250411.9727 | 1250411.9727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certified net | 0 | 4287126.7636 | 4287126.7636 | 7716828.1745 | 8574253.5273 | 11146529.5855 | 12861380.2909 | 14576230.9964 | 17148507.0545 | 17720123.9564 | 20006591.5636 | 20006591.5636 | 20006591.5636 | 20006591.5636 | 18863357.76 | 18577549.3091 | 17720123.9564 | 17148507.0545 | 16005273.2509 | 14290422.5455 | 13432997.1927 | 10003295.7818 | 10003295.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Client payment | 0 | 0 | 0 | 4287126.7636 | 4287126.7636 | 7716828.1745 | 8574253.5273 | 11146529.5855 | 12861380.2909 | 14576230.9964 | 17148507.0545 | 17720123.9564 | 20006591.5636 | 20006591.5636 | 20006591.5636 | 20006591.5636 | 18863357.76 | 18577549.3091 | 17720123.9564 | 17148507.0545 | 16005273.2509 | 14290422.5455 | 13432997.1927 | 10003295.7818 | 10003295.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19649331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19649331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advance received | 39298662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LDs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contractor cash flow | 39298662 | -4827845.4545 | -4827845.4545 | -4402995.0545 | -5368564.1455 | -4835570.0073 | -5909282.8364 | -5268144.96 | -6450001.5273 | -5378863.5491 | -5381438.4 | -4809821.4982 | -2523353.8909 | -2523353.8909 | -1235928.4364 | -914072.0727 | -1091736.7855 | -733832.5091 | -303832.4073 | 1055688.8727 | 878024.16 | 3025449.8182 | 21817355.4655 | 10003295.7818 | 10003295.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19649331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative cash | 39298662 | 34470816.5455 | 29642971.0909 | 25239976.0364 | 19871411.8909 | 15035841.8836 | 9126559.0473 | 3858414.0873 | -2591587.44 | -7970450.9891 | -13351889.3891 | -18161710.8873 | -20685064.7782 | -23208418.6691 | -24444347.1055 | -25358419.1782 | -26450155.9636 | -27183988.4727 | -27487820.88 | -26432132.0073 | -25554107.8473 | -22528658.0291 | -711302.5636 | 9291993.2182 | 19295289 | 19295289 | 19295289 | 19295289 | 19295289 | 19295289 | 19295289 | 19295289 | 19295289 | 19295289 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620 | 38944620

## Returns
Contract sum (AED) | 392986620
Margin (AED) | 38944620
Margin on contract | 9.91%
Peak negative cash (AED) | 27487820.88
NPV of the contract (AED) | 30841371.2127
LDs (AED) | 0
Structure and envelope cost (AED) | 138220000
Net profit (AED) | 38944620